## Disclaimer
Issue Log Template
  Disclaimer
  This version of the document and its current content is meant to serve as an example.
  The current example`s content is fictive or adjusted to remove real confidential data and it should not be replicated to the automation of other business processes.
  The list of examples is not exhaustive. Additional entries may be added or removed, case by case, as required to provide relevant data for RPA.

## Order-to-Cash
Issue ID | Issue date opened | Activity name | Test Scenario ID | Environment | Issue Title | Issue Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Current status | Identified By | Issue closed date | Retested By | Retest Date (in case of failure) | Status List
I1 | 2019-03-11 | SO Reply | TS06 | Staging | Reply email not moved to the Processed folder | After attaching the Sales Order to the email, the email is not moved to the Processed folder | 1. Run the automation 2. Navigate to the Processed folder 3. Look for the latest processed item | Once the automation runs and the SO is generated and validated, the SO should be attached to an email and the email should be moved to the "Processed" folder. | The email is not moved to the Processed folder. | Medium | Under Investigation | P.Ionescu |  |  |  | Opened
I2 | [15 empty] | Under Investigation
I3 | [15 empty] | Fixed& retest not started
I4 | [15 empty] | Fixed &Under testing
I5 | [15 empty] | Closed
I6
I7
I8 | [15 empty] | Severity
I9 | [15 empty] | Critical
I10 | [15 empty] | High
Medium
Low

## Issue_ID_1_PS
Insert Prinstscreen 1

## Issue_ID_2_PS
Insert Prinstscreen 2