## Disclaimer
Traceability Matrix Template
  Disclaimer
  This version of the document and its current content is meant to serve as an example.
  The current example`s content is fictive or adjusted to remove real confidential data and it should not be replicated to the automation of other business processes.
  The list of examples is not exhaustive. Additional entries may be added or removed, case by case, as required to provide relevant data for RPA.

## Order-to-Cash
Process Name | Order-to-Cash
Document date | 2019-04-10
[5 empty] | SOLUTION DESIGN | [17 empty] | BUILD | [8 empty] | TESTING | [5 empty] | STABILIZE
ID | Sub-process Name (Activity ) | ID | WBS Activities | Priority | As-Is Process Maps & Details |  |  | Video Recording |  |  | PDD |  |  | Handover to Dev |  |  | Test Scenarios |  |  | Test Data Definition |  |  | Change Requests | [8 empty] | UAT plan |  |  | Testing |  |  | User Manuals |  |  | Training |  |  | Lessons Learned |  |  | Handover Documentation
[5 empty] | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Request Name | Request ID | Request Owner | Date of Submission | Change Description | Reason | Impact | Proposed Action | Status | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date
A | Product Code Retrieval | A.01.01 | Download PO attachment from email | High | Finalised | 2019-02-10 | 30/09/2019 | Finalised | 15/09/2019 | 15/09/2019 | WIP | 13/10/2019 |  | Not started | 16/10/2019 |  | Not started | 18/10/2019 |  | Not started | [11 empty] | Not started | 25/10/2019 |  | Not started | 2019-01-11 |  | Not started | 2019-03-11 |  | Not started | 2019-09-11 |  | Not started | 20/11/2019 |  | Not started | 20/11/2019
|  | A.01.02 | Verify if the product code is present | High | Under validation with SME | 2019-02-10 | [10 empty] | Not started | 18/10/2019 |  | Not started | [14 empty] | Not started | 2019-01-11 |  | Not started | 2019-03-11
|  | A.02 | If NO, lookup product description in Master Data File | High | Under validation with SME | 2019-03-10 |  | Finalised | 15/09/2019 | 15/09/2019 | [6 empty] | Not started | 18/10/2019 |  | Not started | [14 empty] | Not started | 2019-01-11 |  | Not started | 2019-03-11
|  | A.03 | Exception 1 | Medium | Under validation with SME | 2019-03-10 |  | Finalised | 15/09/2019 | 15/09/2019 | [6 empty] | Not started | 20/10/2019 |  | Not started | [14 empty] | Not started | 2019-03-11 |  | Not started | 2019-06-11
|  | A.04 | Exception 2 | Medium | Under validation with SME | 2019-03-10 |  | Finalised | 15/09/2019 | 15/09/2019 | [6 empty] | Not started | 20/10/2019 |  | Not started | [14 empty] | Not started | 2019-03-11 |  | Not started | 2019-06-11
B | Open SAP | B.01 | Insert Transaction Type | High | WIP | 2019-05-10 |  | Finalised | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 20/10/2019 |  | Not started | [14 empty] | Not started | 2019-03-11 |  | Not started | 2019-06-11
|  | B.02 | Insert Sales Organization Details values | High | WIP | 2019-05-10 |  | Finalised | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 20/10/2019 |  | Not started | [14 empty] | Not started | 2019-03-11 |  | Not started | 2019-07-11
|  | B.03 | Insert Volumes Details values | High | WIP | 2019-05-10 |  | Finalised | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 20/10/2019 |  | Not started | [14 empty] | Not started | 2019-03-11 |  | Not started | 2019-07-11
C | Generate SO | C.01 | Generate SO | Medium | WIP | 2019-06-10 |  | Finalised | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 24/10/2019 |  | Not started | [14 empty] | Not started | 2019-06-11 |  | Not started | 2019-07-11
|  | C.02 | Validate SO | Medium | WIP | 2019-06-10 |  | Finalised | 16/09/2019 | 16/09/2019
|  | C.03 | Exception 1 | Low | WIP | 2019-06-10 |  | Not started | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 24/10/2019 |  | Not started | [14 empty] | Not started | 2019-06-11 |  | Not started | 2019-07-11
D | Respond to Order | D | Reply to order email with SO attached | Medium | WIP | 2019-06-10 |  | Finalised | 16/09/2019 | 16/09/2019 | [6 empty] | Not started | 24/10/2019 |  | Not started | [14 empty] | Not started | 2019-06-11 |  | Not started | 2019-07-11
E | Archive documentation | E | Introduce file archive data in the dedicated app | Low | Not started | 2019-09-10 |  | Not started | 20/09/2019 | [7 empty] | Not started | 24/10/2019 |  | Not started | [14 empty] | Not started | 2019-06-11 |  | Not started | 2019-07-11